IT ARCHITECTURE RISK REGISTER

Enterprise Architecture Program — PT Equity Life Indonesia

| Nomor Dokumen | ELI-EA-RISK-2025-001 |
| --- | --- |
| Versi | 1.0 |
| Tanggal | April 2025 |
| Pemilik Dokumen | Chief Enterprise Architect + Chief Risk Officer |
| Review Cycle | Bulanan oleh ARB, Quarterly oleh Risk Committee |
| Framework | ISO 31000, COBIT 2019, NIST CSF 2.0 |

## 1. RISK TAXONOMY

| Kategori Risiko | Sub-Kategori | Contoh Risiko |
| --- | --- | --- |
| Strategic Risk | Technology Strategy | Pilihan teknologi yang tidak sesuai tren industri jangka panjang |
| Operational Risk | System Availability | Downtime sistem core yang mempengaruhi layanan nasabah |
| Security Risk | Cyber Threat | Ransomware, data breach, social engineering |
| Compliance Risk | Regulatory | Ketidakpatuhan terhadap POJK, UU PDP, atau OJK audit finding |
| Delivery Risk | Project Execution | Timeline slip, cost overrun, scope creep dalam proyek transformasi |
| Vendor Risk | Third-party Dependency | Vendor lock-in, vendor bangkrut, SLA breach dari vendor kritis |
| Data Risk | Data Quality & Privacy | Data corruption, kehilangan data nasabah, privacy breach |
| Integration Risk | System Integration | Kegagalan integrasi dengan sistem mitra (bank, BPJS, OJK) |

## 2. RISK REGISTER — ARCHITECTURE RISKS

| Risk ID | Deskripsi Risiko | Kategori | Prob (1-5) | Dampak (1-5) | Risk Score | Status | Mitigasi | Owner |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RISK-001 | Core Legacy System failure sebelum pengganti siap | Operational | 4 | 5 | 20 — KRITIS | ACTIVE | Parallel running PAS baru. DR plan. 24/7 monitoring legacy. | CTO |
| RISK-002 | Data breach nasabah via aplikasi baru | Security | 3 | 5 | 15 — KRITIS | ACTIVE | Penetration testing, WAF, encryption at rest, SIEM monitoring. | CISO |
| RISK-003 | Ketidakpatuhan OJK — laporan terlambat | Compliance | 3 | 5 | 15 — KRITIS | ACTIVE | Build automated OJK Reporting Engine. Parallel manual backup. | CRO |
| RISK-004 | Data migration error — kehilangan data polis | Data | 2 | 5 | 10 — TINGGI | MONITORED | Triple validation, parallel running 60 hari, backup lengkap pre-migration. | Data Architect |
| RISK-005 | Vendor implementor gagal deliver (capability/finansial) | Vendor | 3 | 4 | 12 — TINGGI | ACTIVE | Escrow code, knowledge transfer wajib, backup vendor identified. | PMO |
| RISK-006 | API Bancassurance tidak compatible dengan core baru | Integration | 3 | 4 | 12 — TINGGI | ACTIVE | E2E integration testing dengan semua mitra sebelum cutover. | Integration Lead |
| RISK-007 | Resistensi tinggi dari agen terhadap portal baru | Operational | 4 | 3 | 12 — TINGGI | ACTIVE | Change management program, champion network, incentive untuk early adopter. | Change Manager |
| RISK-008 | Cost overrun program transformasi > 30% | Delivery | 3 | 4 | 12 — TINGGI | MONITORED | Fixed-price contract untuk komponen tertentu. Monthly budget review. | CFO + PMO |
| RISK-009 | Performance degradasi di peak bulan | Operational | 3 | 3 | 9 — SEDANG | MONITORED | Load testing 200%, auto-scaling, capacity planning quarterly. | Infra Architect |
| RISK-010 | Shadow IT — unit bisnis beli tool tanpa EA review | Strategic | 4 | 3 | 12 — TINGGI | ACTIVE | Policy shadow IT, mandatory EA review, procurement gate. | CEA |
| RISK-011 | Key person risk — CEA atau Data Architect resign | Strategic | 3 | 4 | 12 — TINGGI | MONITORED | Knowledge documentation, succession plan, backup roles identified. | HR + CTO |
| RISK-012 | Serangan ransomware ke infrastructure baru | Security | 2 | 5 | 10 — TINGGI | MONITORED | Air-gapped backup, EDR di semua endpoint, incident response drill. | CISO |

## 3. RISK HEAT MAP — SUMMARY

| Risk Score | Klasifikasi | Jumlah Risiko | Action Required |
| --- | --- | --- | --- |
| 15–25 | KRITIS | 3 risiko | Immediate action — eskalasi ke CTO/BOD, mitigasi segera |
| 10–14 | TINGGI | 7 risiko | Active monitoring — mitigasi dalam 30 hari, laporan ke ARB monthly |
| 5–9 | SEDANG | 2 risiko | Monitor quarterly — mitigasi dalam rencana project |
| 1–4 | RENDAH | 0 risiko | Accept — review tahunan |