## ISO 27001_2022
No | Main Activities | Maret |  |  |  | April |  |  |  | Mei |  |  |  | Juni |  |  |  | Juli
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Preparation
1 | RTM - Persiapan ISO Presentasi pada BOM dan Penentuan Ruang Lingkup
2 | Pengajuan & Approval Budget Penentuan Badan Sertifikasi & Approval Budget
3 | Kick Off Tim SMKI Internal
4 | Awareness Training Karyawan ELI
5 | Request For Audit
6 | Mengirimkan Dokumen Awal ke Badan Sertifikasi
7 | Audit Notification dari Badan Sertifikasi
Persiapan Dokumen Awal
1 | Penentuan Aset Per Departemen Terkait
2 | Penentuan Risiko Per Departemen Terkait
3 | Review Sasaran Keamanan Informasi Per Dept
4 | Review ROPA & DPIA Per Dept
5 | Review Dokumen Per Dept
Persiapan Dokumen & Teknis
1 | DR Application Preparation
2 | Minor Testing
3 | Revisi Dokumen Per Departemen
Audit & Sertifikasi
1 | Internal Audit
2 | Tinjauan Management
3 | External Audit
4 | External Audit (Remediation)
5 | External Audit (Final)
6 | Presentasi Final Report Pada Management
|  |  | Sedang Berjalan |  |  |  | Sudah Selesai
|  |  | Penambahan |  |  |  | Belum Berjalan
100%
MR & DC
100%
Endiaz L.A
100%
All Team
100%
MR & DC
100%
MR & DC
100%
MR & DC
100%
MR & DC (Note: 11 - 12 Juni )
20%
All Team
20%
All Team
0%
All Team
0%
All Team
0%
All Team
30%
0%
IT & BCDRP Team
0%
All Team
0%
Internal Audit
0%
All Team
0%
TSI International
0%
0%
0%
TSI International
TSI International
All Team

## Progress Data Awal
Tracking Penyelesaian Dokumen Awal Keperluan ISO 27001:2022
| Sasaran Keamanan Informasi | Klasifikasi Aset + Owner | Risk Register | Document Review | Business Impact Analysis | ROPA | DPIA | Hak Akses | Kebijakan | SOP | Instruksi Kerja | Forms | Bukti Implementasi |  | Catatan
MR & DC | N/A | N/A | N/A |  | N/A | N/A | N/A | N/A
CeXs
General Affair
Human Capital
Internal Audit | ✅ | ✅ |  | ✅ | ✅ | ✅ |  |  | N/A | ✅ | ✅ | ✅ | ✅
Information Technology |  | ✅ | ✅ | ✅ | ✅ | ✅ |  |  | ✅ | ✅ | ✅ | ✅ |  | On going persiapan perubahan SOP dan penyiapan evidence
Legal&Compliance | ✅ | ✅ |  | ✅ |  | ✅ |  |  | N/A | ✅ | ✅
Claim
NBUW Institutional
Risk Management
SBU Retail
| 20% | 30% | 10% | 27.27% | 20% | 30% | 0% | 0% | 11.11% | 27.27% | 27.27% | 18.18% | 9.091%